## Instructions
		Using the Status tracker

At the end of each week, update the status of all activities completed during the week
The status tracker shown in this worksheet is an example tracker (values filled are during the middle of the week)
Fill in hours spent on each activity during the current week
	If 5 team members each spent an hour, that counts as 5 hours
	Fill in time for activities not fully completed ("ongoing") as well, then update these values during following weeks
During the planning phases, identify the activities to be done during each week
If you spend time on an activity not listed in the tracker, add the activity and list actual hours (need not fill in estimated hours if you didn't estimate it up front)

For new activities, identify the type of activity - documentation, coordination, estimation etc.

At the end of each week, plan ahead for the following week
	Identify people responsible for each activity
	Estimate the hours needed for the activity

TEAM NAME	Team 30 Project 1
PROJECT NAME	Robustest is a self service testing tool. / It is a tool on the cloud for Web and Mobile automation.
PROJECT MENTOR	Mr. Reddy Raja,Mr. Om Narayan
TEAM MEMBERS	Pooja Shamili Ganti
	Kavya Nerella
	Vishal Gupta
	Shubham Ghiya
	Team

## Team_Status
TEAM NAME	Team 30 Project 1
PROJECT NAME	Robustest is a self service testing tool. / It is a tool on the cloud for Web and Mobile automation.
PROJECT MENTOR	Mr. Reddy Raja,Mr. Om Narayan

Activity Name	Type	Responsible	Estimated Team Hours	Actual Hours	Status	Comments	Estimation error	Estimation error %
See Instructions sheet for usage
Week 6 (sept 8- sept 14)
Learn locust	Preparation	Vishal	20	10	Done		10	100
Role preferences	Coordination	Pooja	0.5	0.3	Done		0.2	66.6666666667
Git Repository setup	Preparation	Shubham	1	1.5	Done		-0.5	33.3333333333
Discuss Requirements	Documentation	Shubham	1.5	3	Done		-1.5	50
Research existing technology	Preparation	Vishal	10	9	Done		1	11.1111111111
Project synopsis writeup	Documentation	Kavya	2	1	Done		1	100
Identify role owners	Preparation	Team	2	1.5	Done		0.5	33.3333333333
Team Meeting	Coordination	Team	2	0.5	Done		1.5	300
Status tracker	Documentation	Kavya	1	0.6	Done		0.4	66.6666666667
Week 7 (sept 15 - sept 21)
Locust Benchmarking	Design	Vishal	4	3	Done		1	33.3333333333
JMeter Benchmarking	Design	Kavya	4	5	Done		-1	20
Document SRS	Requirements	Team	6	5	Done		1	20
Mentor Meeting	Coordination	Team	0.5	0.5	Done		0	0
Client Meeting	Coordination	Team	0.5	0.5	Done		0	0
Multiprocessing Benchmarking	Design	Shubham	8	9	Done
Python Events Benchmarking	Design	Pooja	6	7	Done		-1	14.2857142857
Week 8 (sept 22 - sept 28)
Analysis of Gevent	Design	Pooja & Kavya	5	5	Done		0	0
Analysis of Multiprocessing	Design	Shubham & Vishal	3	1	Done		2	200
Test Plan	Design	Team	2	2	Done
Week 9 (Sept 29 – Oct 5)
Gevent Benchmarking	Design	Pooja Vishal	20	10	Done
Multiprocessing Benchmarking	Design	Shubham Kavya	20	15	Done		5	33.3333333333
Prepare Design Document	Design	Team	3	2	Done		1	50
Week 10 (Oct 6 – 12)
Gevent Benchmarking	Design	Pooja Vishal	20	10	Done		10	100
Multiprocessing Benchmarking	Design	Shubham Kavya	20	15	Done		5	33.3333333333
Team Meeting	Coordination	Team	2	2	Done
Client Meeting	Coordination	Team	1	1	Done		0	0
Week 11 (Oct 13 – 19)
Client Meeting	Coordination	Team	2	2	Done		0	0
Team Meeting	Coordination	Team	4	6	Done		-2	33.3333333333
Fix Things	Development	Team	5	4	Done
Prepare Presentation	Delivery	Team	4	4	Done		0	0
Week 12 (Oct 20 - Oct 26)
Client Meeting	Coordination	Team	1	1	Done		0	0
Team Meeting	Coordination	Team	1	1	Done		0	0
Week 13 (Oct 27 – Nov 2)
Client Meeting	Coordination	Team	1	1	Done		0	0
Team Meeting	Coordination	Team	1	1	Done		0	0
Discuss Architecture	Interfaces	Team	4	3	Done		1	33.3333333333
Week 14 (Nov 3 – 9)
Client Meeting	Coordination	Team	6	6	Done		0	0
Team Meeting	Coordination	Shubham	5	6	Done		-1	16.6666666667
Implement Master	Development	Pooja	20	40	Done		-20	50
Implement Requests Module	Development	Vishal	20	15	Done
Implement Slaves	Development	Kavya	20	30	Done		-10	33.3333333333
Utility Stuff and Sandbox	Development	Shubham	20	20	Done
Week 15 (Nov 10 – 16)
Client Meeting	Coordination	Team	6	6	Done		0	0
Team Meeting	Coordination	Team	20	25	Done		-5	20
Finish Master	Development	Pooja	20	30	Done		-10	33.3333333333
Finish Slave	Development	Kavya	20	20	Done
Finish Requests Module	Development	Vishal	20	15	Done
Develop UI	Interfaces	Shubham	40	35	Done
Integrate All Modules	Delivery	Team	30	30	Done
Week 16 (Nov 17 – Nov 23)
Prepare Presentation	Delivery	Team	10	8	Done		2	25
Client Meeting	Coordination	Team	5	30	Done		-25	83.3333333333
Team Meeting	Coordination	Team	5	20	Done		-15	75
Testing	Testing	Team	60	80	Done
Week 17

## Individual_Status
TEAM NAME	Team 30 Project 1
PROJECT NAME	Robustest is a self service testing tool. / It is a tool on the cloud for Web and Mobile automation.
PROJECT MENTOR	Mr. Reddy Raja,Mr. Om Narayan

Actvities	Pooja Shamili Ganti		Kavya Nerella		Vishal Gupta		Shubham Ghiya		Team		Estimated Total Hours	Actual Total Hours
	Estimated Time	Actual Time Spent	Estimated Time	Actual Time Spent	Estimated Time	Actual Time Spent	Estimated Time	Actual Time Spent	Estimated Time	Actual Time Spent
Week 6 ( sept 8 – sept 14)
Learn locust					20	10					20	10
Role preferences	0.5	0.3					0.5	0.3
Git Repository setup						1	1.5			1	1.5
Discuss Requirements						1.5	3			1.5	3
Research existing technology					10	9					10	9
Project synopsis writeup			2	1					2	1
Identify role owners			2	1.5					2	1.5	4	3
Team Meeting	2	0.5	2	1.5					4	2
Status tracker			1	0.6					1	0.6
Week 7 ( sept 15 – sept 21)
Locust Benchmarking					4	3					4	3
JMeter Benchmarking			4	5					4	5
Document SRS			6	5					6	5	12	10
Mentor Meeting			0.5	0.5					0.5	0.5	1	1
Client Meeting			0.5	0.5					0.5	0.5	1	1
Multiprocessing Benchmarking						8	9
Python Events Benchmarking	6	7					6	7
Week 8 ( sept 22 – sept 28)
Analysis of Gevent	5	5					5	5
Analysis of Multiprocessing			5	5	3	1	3	1			11	7
Test Plan			2	2					2	2
Week 9 ( sept 29 – oct 4)						0	0
Multiprocessing Benchmarking			20	15					20	15
Gevent Benchmarking	20	20
Prepare Design Document			3	2					3	2	6	4
Week 10 (Oct 6 – 12)						0	0
Gevent Benchmarking	20	20					20	20
Multiprocessing Benchmarking			20	15					20	15
Team Meeting			2	2					2	2
Client Meeting			1	1					1	1
Week 11 (Oct 13 – 19)						0	0
Client Meeting			2	2					2	2
Team Meeting			4	6					4	6
Fix Things			5	5					5	5
Prepare Presentation			4	4					4	4
Week 12 (Oct 20 - Oct 26)						0	0
Client Meeting			1	1					1	1
Team Meeting			1	1					1	1
Week 13 (Oct 27 – Nov 2)						0	0
Client Meeting			1	1					1	1
Team Meeting			1	1					1	1
Discuss Architecture			4	3					4	3
Week 14 (Nov 3 – 9)						0	0
Client Meeting			6	6					6	6
Team Meeting			5	6					5	6
Implement Master	20	20					20	20
Implement Requests Module					20	20					20	20
Implement Slaves			20	20					20	20
Utility Stuff and Sandbox						20	20			20	20
Week 15 (Nov 10 – 16)						0	0
Client Meeting			6					6	0
Team Meeting			20					20	0
Finish Master						0	0
Finish Slave			20					20	0
Finish Requests Module						0	0
Develop UI						0	0
Integrate All Modules						0	0
Week 16 (Nov 17 – Nov 23)						0	0
Prepare Presentation						0	0
Client Meeting						0	0
Team Meeting						0	0
Week 17						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0